## CHEF High Level Tasks
VSTF# | CHEF Area | Task Detail | Task Owner | Task Associates | Timeline | Comments
| Metadata Management | Create a single XML metadata file | Ram | Guru, Kailash, Ravi | 16th Aug 2010 | This is a core task on which many other tasks depends, hence of very high importance. The expectation is to finish the 1st cut by 6th Aug and improve over period of time. Ravi may help Ram in creating Automated Test/Unit Test for this XML file.
| Core Engine | Create Dynamic SSIS package from the XML metadata file at run time | Rishi | Kailash, Smita | 16th Aug 2010 | This task needs to go hand in hand with the XML metadata to achieve quick progress. Ideally at the end of every day, this engine may be tested against a sample XML file. Smita may help in Automating the Test/Unit Test for this activity. The 1st Cut should be ready by 6th Aug and the basic SSIS package creation should be completed by 16th Aug.
| Operations Dashboard | Create a Web UI for CHEF Operations Tasks | Kailash | Jayant, Jyoti, Smita, Bala | 16th Aug 2010 | This would be the interface from which all actions/requests to the Core Engine will be submitted apart from Tracking Task History. This too will go hand in hand alongwith XML metadata. The 1st cut of this UI should be ready by 16th Aug. Smita may help in Automating the Test/Unit Test for this activity
| Control Structure | Create the Control Mechanism to manage CHEF | Balaji | Jyoti, Murli, Ravi | 16th Aug 2010 | This is a fairly independent task and should be over by 16th Aug. Additional enhancements may continue in future based on the need and XML metadata. Balaji would be temp. Task owner for this. Ravi may help in Automating the Test/Unit Test for this activity.
| Deployment | Create a Deployment package for Installing CHEF | Ram | Jyoti, Ravi | 30th Sep 2010 | This needs to be ready by the time CHEF hits Beta stage. Ravi may help in Automating the Test/Unit Test for this activity.

## CHEF Detailed Task List
VSTF# | CHEF Area | Task | Task Owner | Assigned To | Timeline | Comments
1056 | Metadata Management | Metadata for Table to Table Operation | Ram |  | 03/08/2010
1057 | Metadata Management | Metadata for Flat File to Table Operation | Ram |  | 03/08/2010
1058 | Metadata Management | Metadata for Excel File to Table Operation | Ram |  | 03/08/2010
1059 | Metadata Management | Metadata for Data Flow Task Transformation | Ram |  | 04/08/2010
1060 | Metadata Management | Metadata for SQL Task Transformation | Ram |  | 04/08/2010
1061 | Metadata Management | Metadata for SSIS Task Transformation | Ram |  | 04/08/2010
1062 | Metadata Management | Metadata for Source having SP and Target as Table | Ram |  | 05/08/2010
1063 | Metadata Management | Metadata for Source having SQL Query and Target as Table | Ram |  | 05/08/2010
1064 | Metadata Management | Metadata for Source as Table and Target as Excel File | Ram |  | 05/08/2010
1045 | Core Engine | Create Dynamic SSIS Package Executing a given SSIS package | Rishi | Rishi | 16/08/2010
1046 | Core Engine | Create Dynamic SSIS Package having one or more SQL Tasks | Rishi | Kailash | 16/08/2010
1047 | Core Engine | Create Dynamic SSIS Package having one or more Data Flow Tasks with Source as Table/View and Destination as Table | Rishi | Kailash | 16/08/2010
1048 | Core Engine | Create Dynamic SSIS Package having sequence of Tasks viz., SQL Task followed by Data Flow Task followed by SQL Task | Rishi | Kailash | 16/08/2010
1049 | Core Engine | Create Dynamic SSIS Package having one or more Data Flow Tasks with Source as Flat File and Destination as Table | Rishi | Rishi | 16/08/2010
1050 | Core Engine | Create Dynamic SSIS Package having one or more Data Flow Tasks with Source as Excel File and Destination as Table | Rishi | Rishi | 16/08/2010
1051 | Core Engine | Create Dynamic SSIS Package having one or more Data Flow Tasks with Source as SQL Task having SP and Destination as Table | Rishi | Kailash | 16/08/2010
1052 | Core Engine | Create Dynamic SSIS Package having one or more Data Flow Tasks with Source as SQL Task having SQL Query and Destination as Table | Rishi | Kailash | 16/08/2010
1053 | Core Engine | Create Dynamic SSIS Package having Logging turned on based on the Flag | Rishi |  | 16/08/2010 | Need clarification
1054 | Core Engine | Wrapper for trigering FeedStore Pull | Rishi | Rishi | 16/08/2010
1055 | Core Engine | Create Dynamic SSIS Package having one or more Data Flow Tasks with Source as Web Service and Destination as Table | Rishi | Kailash | 16/08/2010 | Need clarification around logging in tables. Table logging will be done by SQL task.
1065 | Operations Dashboard | Design the Layout | Kailash |  | 04/08/2010
1066 | Operations Dashboard | Design the Web Controls to Display the Progress Status for any given Process | Kailash |  | 04/08/2010
1067 | Operations Dashboard | Design the Class Libraries for the Common Tasks | Kailash |  | 09/08/2010
1068 | Operations Dashboard | Design the Parsing and Reading the XML Metadata Strategy | Kailash |  | 10/08/2010
1069 | Operations Dashboard | Develop the Common Utility Classes | Kailash |  | 11/08/2010
1070 | Operations Dashboard | Develop the UI Controls | Kailash |  | 12/08/2010
1071 | Operations Dashboard | Develop the UI Reports/history | Kailash |  | 13/08/2010
1072 | Operations Dashboard | Develop the utility for reading & displaying the Windows Event Viewer | Kailash
1073 | Operations Dashboard | Develop the utility for reading & displaying the verbose flat file SSIS log | Kailash
1074 | Operations Dashboard | Develop the utility for reading & displaying the Failed Data(in flat files) during Data Loading Operation | Kailash
1075 | Operations Dashboard | Design and Develop the Flat File Loading Operations from UI | Kailash
1076 | Operations Dashboard | Design and Develop the Flat File Correction and Re-Loading Operations from UI (for files that comes to Landing Pad, not necessarily the files that were loaded using UI by the Users) | Kailash
1077 | Operations Dashboard | Design to store the Flat files loaded using SQL 2008 FileStream(?) | Kailash
1078 | Control Structure | Create the Table Schema for Global Metadata Configurations for CHEF | Balaji/Jyoti |  | 6th Aug 2010
1079 | Control Structure | Create the Table for Common Logging & Archiving | Balaji/Jyoti |  | 6th Aug 2010
1080 | Control Structure | Create the Table for Action Queue | Balaji/Jyoti |  | 6th Aug 2010
1081 | Control Structure | Create the UDF/View/SP to Parse the XML Metadata and Display results in Tabular format | Balaji/Jyoti |  | 16th Aug 2010
1082 | Control Structure | Create the Common SPs for Log Insert | Jyoti/Balaji |  | 6th Aug 2010
1083 | Control Structure | Create the Common SPs for Action Insert (that would be used by UI/External System to put a request to Queue) | Murli/Balaji |  | 6th Aug 2010
1084 | Control Structure | Create the UDF/SP for reading and displaying Log in user friendly format | Balaji/Jyoti |  | 6th Aug 2010
1085 | Control Structure | Create the SQL Jobs for Control mechanism | Murli/Balaji |  | 16th Aug 2010
1086 | Control Structure | Create Automated Unit Test Cases for each of the Tasks | Jyoti/Balaji |  | 16th Aug 2010
1087 | Control Structure | Create Automated Test for End-to-End Testing | Jyoti/Balaji |  | 16th Aug 2010
1088 | Deployment | Design the Deployment Strategy | Ram |  | 11/08/2010
1089 | Deployment | Develop the Deployment Package for Installing the entire CHEF | Ram |  | 13/08/2010
1090 | Deployment | Add the Capability to update CHEF Configuration Values during Installation | Ram |  | 16/08/2010